## Simple Gantt Chart - EX
BANGKIT FINAL PROJECT B21-CAP0170
| PROJECT TITLE | Symptoms Based Disease Prediction and Its Treatments
| APP NAME | Hipotesa
| DUE DATE | 2021-06-02
| TEAM ID | B21-CAP0170
[8 empty] | 3 MAY - 7 MAY |  |  |  |  | 10 MAY - 14 MAY |  |  |  |  | 17 MAY - 21 MAY |  |  |  |  | 24 MAY - 28 MAY
| TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
| ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28
| 1 | CLOUD COMPUTING | [5 empty] | CLOUD COMPUTING
| 1.1 | Survey Cloud Resources |  | 2021-05-01 | 2021-05-08 | 7 | 100%
| 1.2 | Summary |  | 2021-05-09 | 2021-05-11 | 2 | 100%
| 1.3 | Cloud Arcitecture Plan |  | 2021-05-12 | 2021-05-15 | 3 | 100%
| 1.4 | Cloud Arcitecture Implementation |  | 2021-05-16 | 2021-05-22 | 6 | 100%
| 1.5 | Architectural review |  | 2021-05-23 | 2021-05-28 | 5 | 100%
| 2 | ANDROID DEVELOPMENT | [5 empty] | ANDROID DEVELOPMENT
| 2.1 | Design UI/UX |  | 2021-05-03 | 2021-05-10 | 7 | 100%
| 2.2 | View Model |  | 2021-05-11 | 2021-05-15 | 4 | 100%
| 2.3 | Content Provider |  | 2021-05-16 | 2021-05-20 | 4 | 100%
| 2.4 | API Implementation |  | 2021-05-21 | 2021-05-26 | 5 | 100%
| 2.5 | View Binding |  | 2021-05-27 | 2021-05-30 | 3 | 100%
| 3 | MACHINE LEARNING | [5 empty] | MACHINE LEARNING
| 3.1 | Exploring Methods |  | 2021-05-03 | 2021-05-12 | 9 | 100%
| 3.2 | Training Data |  | 2021-05-13 | 2021-05-19 | 6 | 100%
| 3.3 | Comparing Each Methods |  | 2021-05-13 | 2021-05-19 | 6 | 100%
| 3.4 | Implementing The Models |  | 2021-05-17 | 2021-05-21 | 4 | 100%
| 3.5 | Evaluation |  | 2021-05-24 | 2021-05-28 | 4 | 100%